## Slide 1: Workshop 1 – Matt Pocock Skills
Perth AI Club
26th Aug 2026
Prepared by Rafael Avigad and Raj Saddi

## Slide 2: Skill selection strategy
PERTH AI · WORKSHOP · 26 AUG 2026
Go deep on a focused few, not a tour of all ~19 skills — recommendation: a maximum of three.
Ask Matt skill will be used to justify the shortlist — it's the skill that routes you to whichever skill fits your situation.
MANDATORY
Grill with Docs
A relentless interview that sharpens a plan or design — and creates docs (ADRs and a glossary) as it goes.
Why it's mandatory: every attendee leaves with a real artifact, not just a demo — and it forces them to actually understand the codebase before touching it.
PICK 2–3 MORE FROM
Triage · Wayfinder · Code Review · Implement · Prototype
All five are real skills from Matt Pocock's engineering set — one for triaging issues, one for planning oversized work, one for reviewing a diff, one for implementing a spec, and one for throwaway prototypes.

## Slide 3: Candidate skills, at a glance
VERIFIED AGAINST MATTPOCOCK/SKILLS
PERTH AI · WORKSHOP · 26 AUG 2026
Triage
Moves an issue or PR through a state machine of roles — categorise, verify, grill if needed, then write an agent-ready brief.
Fits the ticket-lifecycle framing: attendees start from a bug report, not a blank page.
Wayfinder
Plans work too big for one session as a shared map of decision tickets on the issue tracker, resolved one at a time.
Covers the "larger, open-ended" side, if the exercise grows past a single bug fix.
Code Review
Reviews a diff against a fixed point on two axes — coding standards and the original spec — via two parallel sub-agent reviews.
A natural finishing move once students have shipped a change.
Implement
Turns a spec or set of tickets into working code — TDD where possible, typechecks and tests along the way, then hands off to Code Review.
Bridges from ticket to shipped feature — the "build it" step.
Prototype
Throwaway code that answers one design question — a state-model sanity check, or several UI directions to compare side by side.
Good for the more exploratory moments; noted as potentially complex for a first workshop.

## Slide 4: Mapping skills to a realistic workflow
PERTH AI · WORKSHOP · 26 AUG 2026
Structure exercises around a real developer workflow (e.g. a ticket lifecycle, or prototyping) — not a feature-by-feature skill tour.
1
Ask Matt
Route to the right skill for the task
2
Grill with Docs
Explore the problem domain
3
Triage / Wayfinder
Work the ticket in unfamiliar code
4
Code Review
Check it against standards and spec

## Slide 5: Codebase options
PERTH AI · WORKSHOP · 26 AUG 2026
Repo | Stack | Status | Why it fits the workshop
microsoft/python-sample-tweeterapp | Django + React + Postgres | Archived (Dec 2023) | A Twitter-like social app built for a VS Code/Azure devcontainer workflow. Genuinely abandoned and still renders a real UI — the Python pick if the survey leans that way.
dotnet-architecture/eShopOnWeb | C# · ASP.NET Core 8, Clean Architecture / DDD monolith | Archived (Jan 2025) | Microsoft's own DDD/Clean-Architecture reference app — one deployable monolith, well-documented patterns to critique or refactor. Simplest local setup of the three; the safe C# pick.
dotnet/eShop | C# · .NET 10, services-based via .NET Aspire | Active (~10.8k★) | The actively maintained successor to eShopOnWeb, same domain with current patterns — but needs Docker plus the Aspire SDK, most compex of the 2.
All three work as a legacy-modernisation scenario — we plant tickets and bugs against whichever one we pick.
Decision pending: attendee language preference (C# vs Python) will guide the final call.

## Slide 6: Repo & workshop materials
PERTH AI · WORKSHOP · 26 AUG 2026
A dedicated repo (working names: “MPSkills” / “Skills for AI-Native Devs”) will hold the slides, handout, and the skills attendees install.
perth-ai/workshop-mp-skills-for-ai-native-devs: Provides an software development centric applied co…
Starts private, made public within a week of the workshop.
Includes a README, a Python .gitignore, and a Creative Commons license.
Package: a slideshow plus a handout attendees work through during the session.
Scaffold the repo after Friday's in-person planning session.
Slides
The deck to be used on the day
Handout
Step-by-step for attendees
Skills to install
The skills they'll need locally

## Slide 7: Attendee prerequisites & logistics
PERTH AI · WORKSHOP · 26 AUG 2026
A one-page prerequisites flyer goes out ahead of time, covering required installs — including Claude Code and Git.
Room Wi-Fi could be patchy — attendees should complete installs beforehand; the workshop repo link goes out in advance too.
Final prerequisite reminder lands about a day before the workshop.
We have early next week to finalise content and communications.

## Slide 8: Action items
PERTH AI · WORKSHOP · 26 AUG 2026
Owner | Action | Target
Rafael | In-person session to lock the workshop theme and detailed plan | Friday
Rajat | One-page prerequisites flyer (installs incl. Claude Code, Git) | Before workshop
Rajat | Check for language preference (C# vs Python) | This week
Rafael | Initial workshop outline — scenario, skills, schedule | Mon 24 Aug
Rajat | Trial skills locally (incl. Wayfinder); build candidate repos to help choose the codebase | Weekend
Rajat | Share presentation link and gather committee input | After today

## Slide 9: Timeline to workshop day
PERTH AI · WORKSHOP · 26 AUG 2026
Today
Present this plan to committee
Friday
In-person session locks the theme
Weekend
Trial skills, build candidate repos
Mon 24 Aug
Draft workshop outline ready
Tue
Finalise content & comms
~1 day before
Final prerequisites sent
26 Aug, 5:30pm
Workshop — Curtin
Input welcome today
Feedback on the skill shortlist and the codebase direction (Python vs C#) will shape what Raf and Rajat lock in on Friday.